## Project Estimation
Development Project Estimation - Email Shopping Cart Contents
KEY | PHASE | EPIC | STORY | STORY POINTS | T SHIRT SIZE (S/M/L/XL) | LOE (in hours) | STATUS
1 | Analysis and Planning | Analysis and Planning | Review the scope and changes required for email sending feature | 3 | M | 4 | In Progress
Research the changes needed for Print Cart content
2 | Design & Development | Add Email Feature with ability to email the cart contents | Add Button to send Email & Show/hide based on Cart Contents | 1 | XS | 16 | Not yet started
|  |  | Create Bootstrap Modal window | 3 | M
|  |  | Add Functionality to Send Email | 8 | L
|  |  | Close Modal Window | 1 | S
|  | Add Feature to print cart contents | Add Button to Print Cart Contents & Show/hide based on Cart Contents | 1 | XS | 8 | Not yet started
|  |  | Write functionality to Print Cart Content | 5 | M
3 | UAT Testing | Test Execution/Automation & User Acceptance Testing | Testing the Email feature & User Acceptance | 3 | S | 8 | Not yet started
|  |  | Testing the Print feature & User Acceptance | 3 | S
4 | Implementation & Deployment | Implementation | Deployment Plan and publish Changes with Verion control | 2 | S | 2 | Not yet started
5 | Technical & Training Documentation | Documentation | Technical Documentation
|  |  | Total Story Points: | 30
|  |  | Total Hours to complete Development Tasks: | 38
|  |  | Number of Days to complete Development Tasks | 4.75
*Note that the actual estimation will be calculated based on the actual hours & availability of Developers/Tester in a SCRUM team
|  |  | Number of Days to complete Tasks with two developers & peer testing | 2.375
=> Go To Task Tab / More Details

## Task
Back To Project Estimation
KEY | STORY | TASK | LOE (in hours) | DESCRIPTION
1 | Review the scope and changes required for email sending feature | Research Exiting cart content | 1 | Go through existing cart content code and analyze how to reuse
|  | Review existing code of email feature in order confirmation | 1 | Review existing method used to send email
|  | Review Bootstrap Modal Window | 1 | Review existing code that displays modal
2 | Research the changes needed for Print Cart content | Research print functionality | 1 | Find existing code similar print functionality, else come up with new approach
3 | Add Button to send Email & Show/hide based on Cart Contents | Add "Email"button | 0.5 | Add new "Email" button at bottom of the cart page with standard grey CSS
|  | Hide button when cart is empty | 0.5 | Create new method to show button when atleast one item in cart and hide button if cart content is empty
4 | Create Bootstrap Modal window | Create Modal window | 2 | Create modal window with header: "Email Shopping Cart Contents", with two textbox with label "Recipients" and "CC" with "Send" button at the bottom of the popup.
|  | Open modal on "Email" button click | 1 | On Click Add function to open Modal window
5 | Add Functionality to Send Email | Email Validation | 3 | Add code to validate - Recipients field is manatory - Split entered text by comma and semicolon - Email should be in valid format Display "Please enter valid Email." for any invalid inputs
|  | Method to create list of Quick order format | 2 | Create new method to create list of quick order format(Qty,PartNumber) using shopping cart contents
|  | On "Send" button click create MailMessage and use existing method to send email. | 6 | Create mail message with subject, body based on requirement and pass that object to existng method to send email(Order confirmation). Sample MailMessage To: Input from "Recipients" textbox CC: Input from "CC" textbox Subject: Shopping Cart Contents Body: Hi {UserName - Logged in user name or guest}, Your shopping cart contents {Table- List of contents in the cart} We have made shopping easy. Click Quick Order Menu, copy the quick order item details below and paste in "Quick Order" placeholder. Quick Order format(Qty,PartNumber): {List of quick order format} Thank you for shopping.
6 | Close Modal Window | Close modal once email is sent | 1 | Close popup once emails is sent and display success/ Failure message in cart content page
7 | Add Button to Print Cart Contents & Show/hide based on Cart Contents | Add "Print" button | 0.5 | Add new "Print" button at bottom of the cart page next to "Email" button with standard grey CSS
|  | Hide button when cart is empty | 0.5 | Use exising method added for "Email" button to show/Hide
8 | Write functionality to Print Cart Content | Print shopping cart content | 7 | On "Print" button click, Add new method to print shopping cart content
9 | Testing the Email feature & User Acceptance | Test email feature | 2 | Create test scenarios, test cases and execute test case
|  | User acceptance testing | 2 | Perform UAT
10 | Testing the Print feature & User Acceptance | Test email feature | 2 | Create test scenarios, test cases and execute test case
|  | User acceptance testing | 2 | Perform UAT
11 | Deployment Plan and publish Changes with Verion control | Checkin | 0.5 | Checkin with proper comments
|  | Publish code changes | 0.5 | Pulish code to specific folder for release
12 | Technical Documentation | Prepare technical document | 1 | Prepare detailed technical documentation for Email and Print
| Total Hours to complete development Task |  | 38
| Number of Days to complete Development Tasks |  | 4.75